## Sheet1
KARC APPROVAL | KARC PERMIT | GOV'T PERMIT | LOT NUM | STREET | OWNER/ CONTRACTOR | % COMPLETE | Heated SQ. FT. | LANDSCAPE PLAN APPROVAL | EXTERIOR COMPLETION DATE REQUIRED | CER. OF OCC. | NOTES
2022-06-02 | 2022-06-29 | 2022-06-29 | 301R | 287 Hollybrook | Yuskanich/Mayfield | 75% | 6173 | 2024-05-13 | 2024-10-09 |  | Finishing of new space.
2022-10-25 | 2022-10-25 | 2022-10-10 | I3 | 113 Bellshire Dr | North/Aspen-Builders | 100% | 1428* | 2024-04-29 | 2024-02-25 | 2024-11-05 | Home Complete. Waiting on landscaping.
2022-12-07 | 2023-04-04 | 2023-03-03 | 158 | 146 Founders Drive | Pope/Ussery Inc. | 100% | 4434 | 2024-08-16 | 2024-08-04 | 2024-08-31 | Home Complete. Landscaping remains.
2023-01-04 | 2023-01-09 | 2023-01-06 | 22 | Lot 22 Founders Dr | Slebonick/Buchanan | 75% | 6612 | 2024-11-25 | 2024-05-09 |  | Waiting on appliance install, paint & landscaping.
2024-05-08 | 2024-05-16 | 2024-05-08 | 58 | 30 Farwood Ct | Vavalle/Capstone Constr | 75% | 3728 |  | 2025-09-16 |  | Installing cabinets.
2024-06-13 | 2024-06-17 | 2024-06-11 | 54 | 103 Maple Hill Dr. | Tarrant/Associated Bldrs. | 75% | 2574 |  | 2025-10-17 |  | Installing cabinets.
2024-10-28 | 2024-10-31 | 2024-11-22 | 4 | 116 Poplar Loop Dr. | Murray/Masterpiece Bldrs. | 0% | 4186 |  | 2026-03-22 |  | Installing foundation walls.
2024-11-06 | 2024-11-22 | 2024-12-02 | 35 | 115 Founders Dr. | Pasek/Form & Structure Bldrs | 25% | 350* |  | 2026-04-02 |  | Beginning framing of Garage.
2024-11-06 | 2024-11-07 | 2024-12-03 | 97 | 108 Northland Ct. | Raleigh/Regal Builders | 0% | 3720 |  | 2026-04-03 |  | Footings poured & Framing of poured walls underway.
2025-01-02 | 2025-01-14 | 2025-01-03 | 266 | 65 Huntmere Ct. | Pyler/Masterpiece Bldrs. | 0% | 3934 |  | 2026-05-14 |  | Footings poured & Framing of poured walls underway.
2025-01-02 | 2025-01-23 |  | 1 | 607 Overlook Dr. | Sauter/Tinsley & Company | 0% | 3858 |  |  |  | No work has begun.
2025-03-05 |  | 2025-02-27 | 93 | 119 Popular Loop Dr | Farr/Mayfiled | 0% | 3101 |  |  |  | Review & Approved Plans at March 5 meeting.
* Garage with living space above or expansion of living space
|  |  |  | COMPLETION GUIDE | 25% = Start of Framing |  | 50% = House Dried-in
[5 empty] | 75% = Start of interior trim, paint, cabinets |  | 100% = Complete